## Agenda
Week | Dates | Agenda | Estimated Completion | Actual Completion | Hurdles | Integral members | Task to be completed
1 | 19/11/2017 - 26/11/2017 | - Discussion on the layout and design of the system | 2017-12-17 | TBC | - Lack of interaction and updates from Hardware development member - A lack of knowledge on purchasing base components for robot | Hardware testing and assembly: Wee Kiat ! New Hardware testing and assembly: Richard & Stephen Hardware and Software Design: Richard Hardware testing and overseer: Stephen Document Control: Richard | Halted. Member delegated to handle Hardware testing went ahead to do Hardware and Software design instead. ! Document access and control to be removed/limited till further notice
2 | 27/11/2017 - 03/12/2017 | - Testing and soldering of board / components - Purchasing of base robot components (Frame and wheels)
3 | 04/11/2017 - 10/12/2017
4 | 11/11/2017 - 17/12/2017
5 | 18/11/2017 - 24/12/2017 | - Hardware fine tuning and fixes - Base programming and testing | 30/12/2017 | TBC |  | Hardware testing and assembly: Richard & Stephen Hardware testing and overseer: Stephen Software testing and overseer: Richard Document Control: Richard
6 | 24/11/2017 - 30/12/2017
7 | 31/12/2017 - 06/01/2018 | - Programming, testing and bug fixes - Fine tuning of firmware design | 13/01/2018 | TBC |  | Firmware coder: Stephen Software testing and overseer: Richard Document Control: Richard
8 | 07/01/2018 - 13/01/2018 | - Final Testing and bug fixes - Compilation of various updates and reports submitted throughout 8 weeks. |  |  |  | Firmware coder: Stephen Report Checker: Stephen Software testing and overseer: Richard Document Control: Richard Report Drafter: Richard